{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["3月报  (2)","4月报 ","5"],"not_rendered":{"external_links":1,"defined_names":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"3月报  (2)","index":0,"n_rows":26,"n_cols":17,"rows_kept":26,"flags":["formulas_cached_only"]}
["兴蜀公司管理项目投资及形象进度完成情况（截止2019年3月底）"]
[{"$nulls":12},"统计：工程部"]
["序号","项目名称","建设规模\n(Km)","概算投资(亿元)","本年计划（亿元）","本月完成（亿元）","本年完成（亿元）","占年计划（%）","开工累计\n完成（亿元）",null,"占概算投资（%）","累计支付金额(万元）","累计形象进度完成情况"]
[{"$nulls":8},"全部","其中\n建安"]
[1,"川九路",123.142,33.3565,10,0.9644,0.9644,0.09644,7.69,5.4519,0.23053977485647478,null,"累计完成：路基土石方45.2万方，占总量的28%，挡防工程26.87万方，占总量的98%，涵洞完成20道，占总量的13%；桥梁桩基完成224根，占总量的82%，梁板预制38片，占总量的16.9%。隧道掘进1737米，占总量10184米的17.1%，二衬完成923米，占总量的9.1%。",null,"        "]
[2,"若九路",169.063,22.4092,5.3739,0.162,0.162,0.030145704237146208,2.1846,1.3629,0.09748674651482428,null,"累计完成：路基土石方72.4万方，占总量的51.2%，挡防工程6.62万方，占总量的31.4%，涵洞完成27%；路面底基层完成总量的11%，基层完成8%；桥梁桩基完成41根，占总量的50%。"]
[3,"漳大路",67.8,3.6783,2.5952,null,null,0]
[4,"扎红隧道","8.36（其中隧道6.41）",6.8307,1.9806,0.3159,0.3159,0.15949712208421693,1.3443,1.1443,0.1968026702973341,null,"累计完成：路基土石方7.61万方，占总量的56.5%；挡防工程1.06万方，占总量的80.3%；桥梁桩基49根，占总量的90.7%；隧道掘进1840米占总量6420米的28.6%，二衬1279米，占总量6420米的19.9%",{"$nulls":3},3]
[5,"茂红路",158,29.8,4,null,null,0]
[6,"理小路",96.1,19.5835,1.936,0.0834,0.0834,0.04307851239669422,2.3657,1.2557,0.1208006740368167,null,"累计完成：路基土石方46.32万方，占总量的15.1%，挡防工程12.49万立方米，占总量的29.3%，涵洞完成8.4%；路面底基层完成8.1%，基层完成4.8%；桥梁桩基29根，占总量的26.6%，梁板预34片，占总量的41.5%，安装34片，占总量的41.5%；隧道掘进76米，占总量7030米的1.1%。"]
[7,"理黑路",64.579,20.5502,0.3107,null,null,0,0.2801,0.1301,0.01363003766386702,null,"累计完成：路基土石方13.2万方,挡防工程完成2.22万方。"]
[8,"迭玛路",98.855,11.4663,4,0.283,0.283,0.07075,3.5345,3.0165,0.3082511359374864,null,"累计完成：路基土石方完成251.5万方，占总量63.2%；挡防完成10.09万方，占总量的44.5%；桥梁桩基成孔93根，占总量的60%；涵洞完成96道，占总量的39.3%；梁板预制完成30片，占总量的9.5%；路面垫层完成总量的4.05%。"]
[9,"唐花路",95.57,5.8033,0.6447,0.1273,0.1273,0.1974561811695362,3.3178,2.6787,0.5717091999379663,null,"累计完成：路基主体工程已完工，底基层完成总量的96.9%，基层完成总量的5.23%；"]
[10,"卓小路",119.532,22.2835,4.4957,null,null,0,1.6273,0.9773,0.07302712769537999,null,"累计完成：路基土石方10.07万方，占总量的3.7%，挡防工程7.88万方，占总量的13.3%，涵洞2道；桥梁桩基45根，占总量的13.6%；隧道掘进63米，占总量4115米的1.5%。",null,null,0.06]
[11,"刷丹路",37,5.61,1.4,null,null,0,0.4741,0.2741,0.08450980392156862,null,"累计完成：路基土石方完成5.34万方，挡防工程4.05万方,涵洞完成7道；桥梁桩基完成14根，梁板预制6片。"]
[12,"乡得路",99.253,25.7759,4.7252,0.3538,0.3538,0.07487513756031491,5.9855,4.9855,0.23221303620824102,null,"累计完成：路基土石方179.52万方，占总量的77.8%，挡防工程28.22万方，占总量的82.2%，涵洞完成总量的79.3%；路面垫层完成27%，底基层完成26.5%，基层完成24%；桥梁桩基完成392根，占总量的86.5%，梁板预制148片，占总量的35.7%，梁片安装69片，占总量的16.7%；隧道掘进911米，占总量8448的10.8%，二衬完成281米，占总量的4.9%。"]
[13,"桑然路",103.14,21.42,2.3,0.104,0.104,0.04521739130434783,11.9918,9.9446,0.5598412698412698,11675,"累计完成：路基土石方305.78万立方米，占总量的100%；挡防工程47.04万立方米,占总量的97.7%，涵洞完成占总量的98%；路面垫层完成94%，底基层完成94%，基层完成94%，下面层完成80.3%，上面层完成2.1%；桥梁桩基186根，占总量的100%，梁板预制270片，占总量的96.1%，安装253片，占总量的90%；隧道掘进3890米，占总量5839米的66.6%，二衬3659米占总量5839米的62.7%",null,null,0.06]
[14,"九石路",143,41.92,3.4026,0.0129,0.0129,0.003791218479985893,1.2126,0.9326,0.028926526717557247,null,"累计完成：路基土石方36.38万方，挡防工程11.15万方，涵洞68道；桥梁桩基完成20根，梁板预制21片，安装18片。"]
[15,"稻木路",26.362,4.31,0.3824,0.2423,0.2423,0.6336297071129706,3.0627,2.5199,0.7106032482598609,null,"累计完成：路基及桥梁主体工程已全部完成，路面底基层完成总量的99.1%，基层完成总量的99.1%，下面层完成总量的98.8%，上面层完成总量的98.7%；"]
[16,"宜达路",134.308,10.3895,2.6838,0.37,0.37,0.1378642223712646,4.0423,3.1723,0.3890755089272824,null,"累计完成：路基土石方363.8万方，占总量的91.3%,挡防工程8.5万方，占总量的89.6%，涵洞完成总量的94.1%；全部桥梁已经完成，路面垫层完成43.3%，底基层31.3%，基层28%，下面层15.1%；"]
[17,"满洛路",72.441,7.968,2.7158,null,null,0,2.6584,2.178,0.3336345381526104,null,"累计完成：路基土石方146.98万方，占总量的90.3%，挡防工程16.82万方，占总量的88%，涵洞完成总量的87.6%；路面垫层完成总量的78%,底基层完成56%，基层完成29%；桥梁桩基完成121根，占总量的96.%，梁片预制64片，占总量的59.2%，梁片安装9片，占总量的8.3%。"]
[18,"石洛路",80.771,6.5763,3.782,null,null,0,null,null,0]
[19,"色泥路",150.981,11.8069,0.3968,null,null,1.1012437677585374,8.2802,7.2677,0.701301781161863,null,"主体工程已基本完工。"]
[20,"色锣路",106.672,9.7665,0.4144,null,null,1.1154032537210108,6.5309,5.6935,0.6687042440997286,null,"主体工程已基本完工。"]
["合计",null,1954.929,321.2898,57.5398,3.0190000000000006,3.0190000000000006,0.05246803082388191,66.5828,52.9856,0.20723595956049648,11675]
[null,"制表：罗淑华",null,null,"复核：",{"$nulls":3},"部门负责人：",{"$nulls":3},"分管领导："]

{"sheet":"4月报 ","index":1,"n_rows":26,"n_cols":14,"rows_kept":26,"merged":[[0,0,0,11],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,3,6],[2,7,3,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[25,1,25,2]],"flags":["formulas_cached_only"]}
["兴蜀公司管理项目投资及形象进度完成情况（截止2019年4月底）"]
[{"$nulls":11},"统计：工程部"]
["序号","项目名称","建设规模\n(Km)","概算投资(亿元)","本年计划（亿元）","本月完成（亿元）","本年完成（亿元）","占年计划（%）","开工累计\n完成（亿元）",null,"占概算投资（%）","累计形象进度完成情况"]
[{"$nulls":8},"全部","其中\n建安"]
[1,"川九路",123.142,33.3565,10,1.1901,2.1545,{"v":0.21545,"d":"21.55%"},8.8801,6.142,{"v":0.2662179785049391,"d":"26.62%"},"累计完成：路基土石方50万方，占总量的31%，挡防工程28.93万方，占总量的98.9%，涵洞完成82道，占总量的54.7%；桥梁桩基完成240根，占总量的87.9%，梁板预制60片，占总量的26.7%,安装16片，占总量的7.1%。隧道掘进2339米，占总量10184米的23%，二衬完成1416米，占总量的13.9%。",null,0.5]
[2,"若九路",169.063,22.4092,5.3739,0.3942,0.5562,{"v":0.10350025121420198,"d":"10.35%"},2.5788,1.5571,{"v":0.11507773592988596,"d":"11.51%"},"累计完成：路基土石方72.7万方，占总量的51.5%，挡防工程7.3万方，占总量的34.8%，涵洞完成29.9%；路面底基层完成总量的17.7%，基层完成12.2%；桥梁桩基完成44根，占总量的53.6%。",null,0.2]
[3,"漳大路",67.8,3.6783,2.5952,0.3491,0.3491,{"v":0.1345175709001233,"d":"13.45%"},0.3491,0.1491,{"v":0.09490797379224099,"d":"9.49%"},"累计完成：路基土石方6.33万方，占总量的5.2%，挡防工程0.28万方，占总量的4.3%。",null,0.2]
[4,"扎红隧道","8.36（其中隧道6.41）",6.8307,1.9806,0.1774,0.4933,{"v":0.24906593961425832,"d":"24.91%"},1.5217,1.3217,{"v":0.22277365423748663,"d":"22.28%"},"累计完成：路基土石方7.61万方，占总量的56.5%；挡防工程1.06万方，占总量的80.3%；桥梁桩基49根，占总量的90.7%；隧道掘进2060,占总量6420米的32.1%，二衬1504米，占总量6420米的23.4%"]
[5,"茂红路",158,29.8,4,null,null,{"v":0,"d":"0.00%"}]
[6,"理小路",96.1,19.5835,1.936,0.1241,0.2075,{"v":0.1071797520661157,"d":"10.72%"},2.4898,1.3798,{"v":0.12713764138177547,"d":"12.71%"},"累计完成：路基土石方54.09万方，占总量的17.7%，挡防工程12.49万立方米，占总量的29.3%，涵洞完成8.4%；路面底基层完成8.1%，基层完成4.8%；桥梁桩基36根，占总量的31.9%，梁板预34片，占总量的41.5%，安装34片，占总量的41.5%；隧道掘进110米，占总量7030米的1.6%。"]
[7,"理黑路",64.579,20.5502,0.3107,0.011,0.011,{"v":0.03540392661731574,"d":"3.54%"},0.2911,0.1411,{"v":0.0141653122597347,"d":"1.42%"},"累计完成：路基土石方15.64万方,挡防工程完成2.29万方。"]
[8,"迭玛路",98.855,11.4663,4,0.2391,0.5221,{"v":0.130525,"d":"13.05%"},3.7736,3.2556,{"v":0.3291035469157444,"d":"32.91%"},"累计完成：路基土石方完成262万方，占总量67%；挡防完成12.09万方，占总量的46.5%；桥梁桩基成孔93根，占总量的60%；涵洞完成96道，占总量的39.3%；梁板预制完成39片，占总量的18%；路面垫层完成总量的15.7%。"]
[9,"唐花路",95.57,5.8033,0.6447,0.0566,0.1839,{"v":0.28524895300139597,"d":"28.52%"},3.3744,2.7353,{"v":0.5814622714662347,"d":"58.15%"},"累计完成：路基主体工程已完工，底基层完成总量的100%，基层完成总量的12.6%；"]
[10,"卓小路",119.532,22.2835,4.4957,0.0201,0.0201,{"v":0.004470938897168405,"d":"0.45%"},1.6474,0.9974,{"v":0.07392914039535979,"d":"7.39%"},"累计完成：路基土石方10.07万方，占总量的3.7%，挡防工程8.11万方，占总量的13.6%，涵洞2道；桥梁桩基46根，占总量的13.9%；隧道掘进110米，占总量3350米的3.2%，二衬完成12米。"]
[11,"刷丹路",37,5.61,1.4,0.0327,0.0327,{"v":0.023357142857142858,"d":"2.34%"},0.5068,0.3068,{"v":0.09033868092691621,"d":"9.03%"},"累计完成：路基土石方完成5.97万方，挡防工程4.55万方,涵洞完成13道；桥梁桩基完成14根，梁板预制9片，安装9片。"]
[12,"乡得路",99.253,25.7759,4.7252,0.5927,0.9465,{"v":0.20030898163040717,"d":"20.03%"},6.5782,5.4782,{"v":0.25520738364130835,"d":"25.52%"},"累计完成：路基土石方189.82万方，占总量的82.2%，挡防工程29.4万方，占总量的85.6%，涵洞完成总量的85%；路面垫层完成36%，底基层完成36%，基层完成34%；桥梁桩基完成406根，占总量的89.6%，梁板预制154片，占总量的37.2%，梁片安装84片，占总量的20.3%；隧道掘进1117米，占总量8448的13.2%，二衬完成540米，占总量的6.4%。",null,0.1]
[13,"桑然路",103.14,21.42,2.3,0.2051,0.3091,{"v":0.1343913043478261,"d":"13.44%"},12.1969,10.0997,{"v":0.5694164332399626,"d":"56.94%"},"累计完成：路基土石方305.78万立方米，占总量的100%；挡防工程47.31万立方米,占总量的98.3%，涵洞完成占总量的100%；路面垫层完成94%，底基层完成94%，基层完成94%，下面层完成80.3%，上面层完成2.1%；桥梁桩基186根，占总量的100%，梁板预制281片，占总量的100%，安装281片，占总量的100%；隧道掘进4056米，占总量5839米的69.5%，二衬3767米占总量5839米的64.5%",null,0.05]
[14,"九石路",143,41.92,3.4026,0.0527,0.0656,{"v":0.019279374595897257,"d":"1.93%"},1.2653,0.9853,{"v":0.03018368320610687,"d":"3.02%"},"累计完成：路基土石方41.58万方，挡防工程11.53万方，涵洞68道；桥梁桩基完成24根，梁板预制21片，安装18片。"]
[15,"稻木路",26.362,4.31,0.3824,0.046,0.2883,{"v":0.7539225941422594,"d":"75.39%"},3.1087,2.5659,{"v":0.7212761020881671,"d":"72.13%"},"累计完成：主体工程已基本完成"]
[16,"宜达路",134.308,10.3895,2.6838,0.1419,0.5119,{"v":0.19073701468067664,"d":"19.07%"},4.1842,3.3142,{"v":0.40273352904374604,"d":"40.27%"},"累计完成：路基土石方363.8万方，占总量的91.3%,挡防工程8.5万方，占总量的89.6%，涵洞完成总量的95.6%；全部桥梁已经完成，路面垫层完成49%，底基层36%，基层29%，下面层15.1%；"]
[17,"满洛路",72.441,7.968,2.7158,0.3134,0.3134,{"v":0.11539877752411812,"d":"11.54%"},2.9718,2.4914,{"v":0.3729668674698795,"d":"37.30%"},"累计完成：路基土石方154万方，占总量的94.7%，挡防工程17.33万方，占总量的90.7%，涵洞完成总量的87.6%；路面垫层完成总量的81.3%,底基层完成56%，基层完成29%；桥梁桩基完成121根，占总量的96.%，梁片预制64片，占总量的59.2%，梁片安装9片，占总量的8.3%。",2.3414,0.15]
[18,"石洛路",80.771,6.5763,3.782,0.3822,0.3822,{"v":0.10105764145954521,"d":"10.11%"},0.3822,0.2323,{"v":0.05811778659732676,"d":"5.81%"},"累计完成：路基土石方61.2万方，占总量的30.6%，涵洞21道，占总量的9.7%。",null,0.15]
[19,"色泥路",150.981,11.8069,0.3968,0.0289,0.0289,{"v":1.1012437677585374,"d":"110.12%"},8.3091,7.2966,{"v":0.701301781161863,"d":"70.13%"},"主体工程已基本完工。"]
[20,"色锣路",106.672,9.7665,0.4144,0.1162,0.1162,{"v":1.1154032537210108,"d":"111.54%"},6.6471,5.8097,{"v":0.6687042440997286,"d":"66.87%"},"主体工程已基本完工。"]
["合计",null,1954.929,321.2898,57.5398,4.4735000000000005,7.492500000000001,{"v":0.13021421694201232,"d":"13.02%"},71.0563,56.2592,{"v":0.22115952638396857,"d":"22.12%"}]
[null,"制表：罗淑华",null,null,"复核：",{"$nulls":3},"部门负责人：",null,null,"分管领导："]

{"sheet":"5","index":2,"n_rows":26,"n_cols":14,"rows_kept":26,"merged":[[0,0,0,11],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,3,6],[2,7,3,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[25,1,25,2]],"flags":["formulas_cached_only"]}
["兴蜀公司管理项目投资及形象进度完成情况（截止2019年5月底）"]
[{"$nulls":11},"统计：工程部"]
["序号","项目名称","建设规模\n(Km)","概算投资(亿元)","本年计划（亿元）","本月完成（亿元）","本年完成（亿元）","占年计划（%）","开工累计\n完成（亿元）",null,"占概算投资（%）","累计形象进度完成情况"]
[{"$nulls":8},"全部","其中\n建安"]
[1,"川九路",123.142,33.3565,10,1.2319,3.3864,{"v":0.33864,"d":"33.86%"},10.112,7.0739,{"v":0.3031493112286961,"d":"30.31%"},"累计完成：路基土石方56.57万方，占总量的35.1%，挡防工程30.09万方，占总量的99.1%，涵洞完成118道，占总量的79%；桥梁桩基完成266根，占总量的97%，梁板预制96片，占总量的42.7%,安装37片，占总量的16.4%。隧道掘进2988米，占总量10184米的29.3%，二衬完成2013米，占总量的19.7%。",null,0.3]
[2,"若九路",169.063,22.4092,5.3739,0.3251,0.8813,{"v":0.16399635274195648,"d":"16.40%"},2.9039,1.8822,{"v":0.12958517037645254,"d":"12.96%"},"累计完成：路基土石方78.1万方，占总量的55.3%，挡防工程8.4万方，占总量的39.8%，涵洞完成30.7%；路面底基层完成总量的20.1%，基层完成15.3%，下面层完成14.5%；桥梁桩基完成48根，占总量的58.5%,梁板预制6片，占总量的6.4%。"]
[3,"漳大路",67.8,3.6783,2.5952,0.2806,0.6297,{"v":0.24264025893958077,"d":"24.26%"},0.6297,0.4297,{"v":0.17119321425658593,"d":"17.12%"},"累计完成：路基土石方18.68万方，占总量的15.4%，挡防工程5万方，占总量的10.6%，涵洞完成20.9%；桥梁桩基完成16根，占总量的100%，梁板预制4片占总量的50%，。"]
[4,"扎红隧道","8.36（其中隧道6.41）",6.8307,1.9806,0.1306,0.6239,{"v":0.3150055538725639,"d":"31.50%"},1.6523,1.4523,{"v":0.24189321738621225,"d":"24.19%"},"累计完成：路基土石方7.8万方，占总量的58%；挡防工程1.06万方，占总量的80.3%；桥梁桩基49根，占总量的90.7%；隧道掘进2225米，占总量6420米的34.6%，二衬1639米，占总量6420米的25.5%"]
[5,"茂红路",158,29.8,4,0.4368,0.4368,{"v":0.1092,"d":"10.92%"},0.4368,0.1368,{"v":0.01465771812080537,"d":"1.47%"},"驻地建设过程中",null,0.3]
[6,"理小路",96.1,19.5835,1.936,0.3639,0.5714,{"v":0.2951446280991736,"d":"29.51%"},2.8537,1.7437,{"v":0.14571961089692853,"d":"14.57%"},"累计完成：路基土石方69.24万方，占总量的22.6%，挡防工程12.88万立方米，占总量的30.7%，涵洞完成8.4%；路面底基层完成8.1%，基层完成10%；桥梁桩基40根，占总量的35.7%，梁板预34片，占总量的41.5%，安装34片，占总量的41.5%；隧道掘进167米，占总量7030米的2.4%。"]
[7,"理黑路",64.579,20.5502,0.3107,0.0182,0.0292,{"v":0.09398133247505633,"d":"9.40%"},0.3093,0.1593,{"v":0.015050948409261225,"d":"1.51%"},"累计完成：路基土石方16.76万方,挡防工程完成2.67万方。"]
[8,"迭玛路",98.855,11.4663,4,0.646,1.1681,{"v":0.292025,"d":"29.20%"},4.4196,3.9016,{"v":0.3854425577562073,"d":"38.54%"},"累计完成：路基土石方完成310万方，占总量78%；挡防完成14.09万方，占总量的62%；桥梁桩基成孔124根，占总量的75%；涵洞完成146道，占总量的60%；梁板预制完成54片，占总量的19%；路面垫层完成总量的15.7%，路面水稳完成总量的15.7%。"]
[9,"唐花路",95.57,5.8033,0.6447,0.1284,0.3123,{"v":0.4844113541181945,"d":"48.44%"},3.5038,2.8637,{"v":0.6037599296951734,"d":"60.38%"},"累计完成：路基主体工程已完工，底基层完成总量的100%，基层完成总量的65%,下面层完成总量的2%。"]
[10,"卓小路",119.532,22.2835,4.4957,0.2302,0.2503,{"v":0.05567542318215184,"d":"5.57%"},1.8776,1.1276,{"v":0.08425965400408374,"d":"8.43%"},"累计完成：路基土石方17万方，占总量的4.5%，挡防工程9.88万方，占总量的16.6%，涵洞2道；桥梁桩基52根，占总量的15.7%；隧道掘进134米，占总量3350米的4%，二衬完成45米，占总量的1.3%。",null,0.1]
[11,"刷丹路",37,5.61,1.4,0.0744,0.1071,{"v":0.0765,"d":"7.65%"},0.5812,0.3812,{"v":0.10360071301247772,"d":"10.36%"},"累计完成：路基土石方完成7.59万方，挡防工程5.27万方,涵洞完成13道；桥梁桩基完成14根，梁板预制9片，安装9片。"]
[12,"乡得路",99.253,25.7759,4.7252,0.5908,1.5373,{"v":0.3253407263184627,"d":"32.53%"},7.169,6.069,{"v":0.2781280188082666,"d":"27.81%"},"累计完成：路基土石方199.1万方，占总量的86.2%，挡防工程31.6万方，占总量的92.1%，涵洞完成总量的86.1%；路面垫层完成50%，底基层完成47%，基层完成47%，下面层完成4%；桥梁桩基完成433根，占总量的95.6%，梁板预制214片，占总量的51.7%，梁片安装157片，占总量的37.9%；隧道掘进1307米，占总量8448的15.5%，二衬完成675米，占总量的8%。"]
[13,"桑然路",103.14,21.42,2.3,0.2446,0.5537,{"v":0.24073913043478262,"d":"24.07%"},12.4415,10.3443,{"v":0.5808356676003734,"d":"58.08%"},"累计完成：路基土石方305.78万立方米，占总量的100%；挡防工程47.4万立方米,占总量的98.5%，涵洞完成占总量的100%；路面垫层完成94%，底基层完成95%，基层完成94%，下面层完成89%，上面层完成57%；桥梁桩基186根，占总量的100%，梁板预制281片，占总量的100%，安装281片，占总量的100%；隧道掘进4206米，占总量5839米的72%，二衬3929米占总量5839米的67.3%"]
[14,"九石路",143,41.92,3.4026,0.043,0.1086,{"v":0.03191676952918356,"d":"3.19%"},1.3083,1.0283,{"v":0.031209446564885494,"d":"3.12%"},"累计完成：路基土石方50.38万方，挡防工程11.8万方，涵洞68道；桥梁桩基完成24根，梁板预制21片，安装18片。"]
[15,"稻木路",26.362,4.31,0.3824,0.0553,0.3436,{"v":0.8985355648535565,"d":"89.85%"},3.164,2.6212,{"v":0.7341067285382832,"d":"73.41%"},"累计完成：主体工程已基本完成"]
[16,"宜达路",134.308,10.3895,2.6838,0.4521,0.964,{"v":0.3591921901781056,"d":"35.92%"},4.6363,3.7663,{"v":0.44624861639154917,"d":"44.62%"},"累计完成：路基土石方396万方，占总量的91.3%,挡防工程9.42万方，占总量的99.3%，涵洞完成总量的97.2%；桥梁已经完成；路面垫层完成69%，底基层完成51.9%，基层完成51.9%，下面层完成26%。"]
[17,"满洛路",72.441,7.968,2.7158,0.4295,0.7429,{"v":0.27354738935120404,"d":"27.35%"},3.4013,2.7709,{"v":0.42686997991967873,"d":"42.69%"},"累计完成：路基土石方159.3万方，占总量的97.8%，挡防工程18.7万方，占总量的92.3%，涵洞完成总量的98.4%；路面垫层完成总量的84%,底基层完成56%，基层完成56%，下面层完成26%；桥梁桩基完成121根，占总量的96.%，梁片预制90片，占总量的83.3%，梁片安装49片，占总量的45%。"]
[18,"石洛路",80.771,6.5763,3.782,0.1428,0.525,{"v":0.13881544156530937,"d":"13.88%"},0.525,0.3751,{"v":0.07983212444687743,"d":"7.98%"},"累计完成：路基土石方71.3万方，占总量的35.6%，挡防工程1.67万方，占总量的14.5%，涵洞60道，占总量的27.7%；路面垫层完成总量的8.8%；桥梁桩基完成33根，占总量的15%。"]
[19,"色泥路",150.981,11.8069,0.3968,0.1306,0.1595,{"v":0.4019657258064516,"d":"40.20%"},8.4397,7.4272,{"v":0.701301781161863,"d":"70.13%"},"主体工程已基本完工。"]
[20,"色锣路",106.672,9.7665,0.4144,0.0667,0.1829,{"v":0.4413610038610039,"d":"44.14%"},6.7138,5.8764,{"v":0.6687042440997286,"d":"66.87%"},"主体工程已基本完工。"]
["合计",null,1954.929,321.2898,57.5398,6.0215000000000005,13.514,{"v":0.23486352055446838,"d":"23.49%"},77.0788,61.4307,{"v":0.23990428578809536,"d":"23.99%"}]
[null,"制表：罗淑华",null,null,"复核：",{"$nulls":3},"部门负责人：",null,null,"分管领导："]